## tracker
ErgJabber Change And Issue Tracker
Summary
Current released Software Version | Beta 2
Issues | 23
New | 7
Investigate | 0
InProgress | 0
InVerificationClo | 9
Closed | 7
Issues
Number | Title | State | Version Reported | Version Fixed | Comments
1 | Software is unable to communicate with PM | Closed | Beta 1 | Beta 2 | Really badly documented interface meant for a long time I was unable to communicate with PM.
2 | key to quick stop speech | Closed | Beta 2 | Beta 3 | Due to windows being stupid about eh control key its easier to use the escape key. I can get the control key to do it if its that important.
3 | keyboard short cut for buttons, particularly report and mute speech | closed | Beta 2 | Beta 3 | Useful when sweaty after a workout keys added from main screen - p = report. d = drag factor. a = PM Information. s = setup. m = mute voice toggle.
4 | save mute state in configuration file | Closed | Beta 2 | Beta 3 | Add to current file.
5 | Access custom program list in programs dialog | InVerificationClo | Beta 2 | Beta 3 | Unfortunately no way to verify this at the moment, as speech doesn't seem to be working. Dialogue just says, custom 1, 2 etc, so not sure what presets if any it is changing.
6 | Update and implement drag factor dialog. | InVerificationClo | Beta 2 | Beta 3 | This screen is used to report the current drag factor. It is set using a physical switch on the machine. If speech is not muted report every 15 seconds to enable user to set the drag factor
7 | Enable speech speed buttons and add volume ones | New | Beta 2 |  | From the setup screen, we may need a tts settings dialog but review current screen layout for best options
8 | When a program is selected speak the current settings before rowing | New | Beta 2 |  | 2 ensure what's been chosen
9 | activity paused code doesn't seem to be working | InVerificationClo | Beta 2 | Beta 3 | Could be a text override issue
10 | All numbers should be rounded to the nearest hole number | InVerificationClo | Beta 2 | Beta 3 | Mainly effects report dialog but a couple in the automatic speech stuff
11 | Speech interrupts its self | InVerificationClo | Beta 2 | Beta 3 | We need to check if we're currently talking and queue if we are. Need to ensure the speech on change stuff doesn't get queued apart from the latest version
12 | Different distance value in report dialog | InVerificationClo | Beta 2 | Beta 3 | There are 2 types of distance reported, this is significant when using the program as the workout distance counts down to 0 and the report dialog needs to show how far we've gone, so counting up
13 | Rework report dialog to show a report as text | InVerificationClo | Beta 2 | Beta 3 | Put all text in to 1 edit area to enable copying to clip board
14 | disable escape key to close | closed | Beta 2 | Beta 3 | program should only be closed by hitting alt f4 or the close click from the title bar
15 | repeat speech short cut key | closed | Beta 2 | Beta 3 | hitting r should just repeat the last thing said
16 | short cut keys 1 to 0 to select program quickly | closed | Beta 2 | Beta 3 | enables power users to start the program, hit the key and go
17 | ability to send reset command | InVerificationClo | Beta 2 | Beta 3 | a button to access the reset functionality, needs short cut key
18 | Ability to setup custom program | New | Beta 2 |  | needs to be worked out with Ed.
19 | Interval training reporting | New | Beta 2 |  | When interval training the user needs to be prompted when to row and stop, should find out what's possible and work with ed to find out what would be useful.
20 | Extra auto speech settings | New | Beta 2 |  | required, 5 minutes and distances of 50, M 250 M 500 M and 1000 M. Doing this as an edit box would be pretty hard but doable if really required, preset values are much easier
21 | reading numbers in program dialog as hole numbers, not digits | InVerificationClo | Beta 2 | Beta 3 | the text printed to the screen was in an odd format, tided up.
22 | XML logging to enable playing back of work out for debug purposes when a PM and rower is not available | New | Beta 2 |  | recording always and playing back when debugging
23 | Heart rate reporting | New | Beta 2 |  | update regular PM call to get this

## lookup
New | Beta 1
Investigate | Beta 2
InProgress | Beta 3
InVerificationClo | release 1.0
Closed